PRIMARY EDUCATION IMPROVEMENT PROJECT (PEIP)

TERMS OF REFERENCE
for
DATA COLLECTION FOR CONDUCTING A TRACER STUDY FOR EMPLOYMENT OUTCOMES OF HIGHER EDUCATION GRADUATES

# Background of the Project

The World Bank has been a partner of choice of the Republic of North Macedonia for over twenty-five years. The Primary Education Improvement Project (PEIP) is aligned with the World Bank Group Country Partnership Framework 2019 – 2023 in North Macedonia which aims to support the country’s ability to achieve faster, inclusive, and sustainable growth and provide its citizens with greater opportunities for a better life. The CPF is organized around three focus areasthat will help North Macedonia (i) improve the environment for a dynamic private sector to enhance export-led growth; (ii) strengthen human capital for inclusive development; (iii) and build sustainability. Specifically, the project will contribute to Focus Area II – Inclusive Growth: Expand Skills and Opportunities for the Most Vulnerable, and CPF Objective 2 –Improve the Quality and Relevance of Education.

According to the World Bank’s 2020 Human Capital Index North Macedonia’s Index is lower than the average for its region and income group. Poor educational outcomes largely explain this loss of lifetime productivity. Children in North Macedonia can expect to complete 11 years of pre-primary, primary and secondary school by age 18. However, when years of schooling are adjusted for quality of learning, the result is equivalent to 7.3 years of education, equivalent to a learning gap of 3.7 years. As noted in the North Macedonia Systematic Country Diagnostic, gaps in human capital start early and expand over time. The education system fails to provide students with the skills they need to successfully complete each stage and move confidently to the next. These challenges persist from preschool education to graduate university degrees, including non-formal education.  With the workforce shrinking and labor productivity low, the country’s future growth will increasingly rely on the formation of human capital.

The Primary Education Improvement Project (PEIP) development objective is to improve conditions for learning in primary education in North Macedonia. The project is organized around three main elements that need to be aligned in order to be complementary to each other. Component 1 focuses on school-level interventions, which are closest to students and most likely to impact learning while also mitigating and recovering learning losses generated by COVID-19.  Component 2 aims to develop a comprehensive national assessment program to inform both school improvement planning and professional development programs, serving to link the school and system levels.  Component 3 is expected to put into practice professional competences for educators. Component 4 would strengthen sector management, project management and monitoring and evaluation.

The Ministry of Education and Science (MOES) is the main implementing agency of the Project in close cooperation with the National Examination Center (NEC), Bureau for Development of Education (BDE) and State Educational Inspectorate (SEI).

# Specific information/background regarding the assignment

The tracer study aims to gather data on the employment outcomes and career trajectories of 2022/2023 graduates of public universities. The data collected will support evidence-based decision-making within the Ministry of education and science, enabling better alignment of higher education programs with labor market demands.

The study will adopt a census-like approach, targeting all graduates from the 2022/2023 academic year. Graduates will receive the questionnaire twice via follow-up contact attempts to maximize the response rate, with a targeted minimum response rate of 30% (approximate number of graduates is 5.000). Additionally, a random sample of graduates will be selected for in-depth phone interviews.

The tracer studies will primarily aim at discussing and answering the following research questions:

- What are the employment status, income levels, types of jobs, and job satisfaction of university graduates about 6-8 months after graduation?

- How do they choose jobs, look for employment, and how are they supported by their university for job search and placement?

- How do graduates assess the knowledge and skills they acquired at university in terms of relevance for their employment?

- What career aspirations do the graduates have? What needs for further education and training do graduates have?

# Objective of the assignment

The objective of this assignment is to hire a qualified firm (Consultant) to conduct a census-based survey of all graduates from the 2022/2023 cohort, collect quality data on their employment outcomes, and perform phone interviews with a representative sample (sample size to be determined). The information gathered will help guide higher education policy and inform adjustments to enrollment quotas.

# Scope of work/Essential duties

The Consultant will be responsible for:

Survey Design and Preparation:

- Assist the expert hired under a separate contract to develop a standardized core questionnaire (in English) in close collaboration with the Ministry of Education and Science (MOES) and the World Bank, ensuring it is suitable for both a census-based email survey and a sample-based phone survey. The questionnaire should take no longer than 15 minutes for administration via phone.

- Translate the questionnaire into Macedonian and Albanian to ensure linguistic and cultural accuracy. The final questionnaire must be approved by MOES and the World Bank before piloting and data collection.

Database Management:

- Develop a secure, organized database to manage contact information for all 2022/2023 graduates, including fields for names, phone numbers, email addresses, study programs, and degree information.

- Coordinate with higher education institutions to validate and update graduate contact information, ensuring data accuracy and completeness.

Sample Selection for Phone Interviews:

- Assist the expert to draw a representative sample from the complete graduate database for the phone survey. The sample should be stratified to reflect diversity across study programs, institutions, and demographics, ensuring it accurately represents the broader graduate population.

- Assist the expert in documenting the sampling process and confirm with MOES that the sample is adequately representative before beginning the phone interviews.

Pilot Testing and Refinement:

- Conduct a pilot test with a small sample of graduates to assess clarity, relevance, and timing, ensuring the survey’s suitability for both email and phone formats. Adjust the survey based on pilot feedback to maximize response rates and data quality.

- Document the pilot process, including participant feedback, and present results and recommended adjustments to MOES for final approval.

Enumerator Training and Preparation:

- Recruit and train enumerators and supervisors for the phone survey.

- Provide clear guidance on technical aspects, such as handling challenges during phone interviews, ensuring enumerators are well-prepared to encourage complete and accurate responses.

Data Collection for Census and Sample Survey:

- Email Census Survey: Distribute the survey via email to all 2022/2023 graduates, with at least two follow-up reminders to boost response rates (via email and/or sms). Reminders should be scheduled strategically to encourage participation without overwhelming recipients.

- Phone Survey Sample: Conduct phone interviews with the selected representative sample of graduates.

Survey Software and Administration:

- Use a reliable online survey platform to administer the email survey, allowing for automated reminders, response tracking, and secure data capture.

- Ensure the platform supports real-time response monitoring and is configured to allow safe data storage and retrieval.

Data Quality Assurance and Entry:

- Implement quality control measures throughout data collection, including random checks on email and phone survey responses to verify accuracy and completeness.

- Ensure accurate entry of phone survey data into the survey platform or compatible software, while email survey responses are automatically captured.

- Conduct plausibility checks on collected data, clean the data set, and code open-ended responses as part of data preparation.

Data Management and Delivery:

- Organize and deliver raw and cleaned data files in SPSS and STATA formats, ensuring consistency and proper documentation for further analysis. Files should include variable labels, value labels, and a comprehensive codebook.

- Provide all necessary syntax files for data processing, including coding of open-ended responses, error correction, and any data quality control scripts used during processing.

# Reporting obligations

The Consultant shall deliver the following outputs:

### 1.	Inception report covering the sections listed below:

  - Questionnaire development and approval;

  - Translation to Macedonian and Albanian language;

  - Database setup and validation;

  - Sample selection;

  - Enumerator recruitment & training

  - Pilot test

2. Report on the data collection phase, the survey data and data documentation, including the sections listed below:

  - Data collection;

  - Census survey (Email);

  - Phone survey (Sample);

  - Data Cleaning and Quality control;

  - Data Quality Assurance and Coding

The report should include: methodology, response rates, challenges encountered, and key findings (summary tables and analysis of findings); breakdowns of responses by demographic and program variables; an analysis of representativeness, comparing respondents to the overall graduate population by key characteristics to assess any response biases. Feedback from MOES and the World Bank must be incorporated before submitting a final version.

### 3. Final Report, including the sections listed below.

Submit a final data codebook and SPSS syntax files for MOES’s reference, along with all data and analysis files as specified in the reporting section.

All reports in English and Macedonian language must be sent for approval to the PEIP Project Director/Client Coordinator.

VI. Qualification requirements

The Consultant shall possess the following relevant qualifications and present documents confirming the qualifications for the purpose of shortlisting:

- The Consultant should be a company or NGO with sufficient number of employees and/or members for conducting field research on the entire territory of the Republic of North Macedonia during the short contract implementation period.

- The company should demonstrate capacity in the planning and logistics for organizing surveys of similar scale. The company should also demonstrate the availability of a network of personnel for data collection and data entry personnel.

- The Consultant should have at least two years of experience in preparing public opinion surveys with 1000 or more respondents in the Republic of North Macedonia. Work experience on projects financed by the World Bank or other international organizations would be considered as an advantage. Similar projects conducted in the area of education and/or employment will also be considered as advantage.

Upon completing the shortlisting phase and selecting the best qualified Consultant, the Consultant shall submit a combined technical-financial proposal that shall also include information of the following key experts:

- a team leader with at least five years research experience and knowledge of the research methods and survey methodology

- at least one team member with excellent knowledge of SPSS, STATA, or other statistic software and experience in coding, entering and processing of the data

- at least one team member (educational specialist) for the needs of conducting surveys in the area of education.

VII. Indicative Timeline for Tracer Study

| Phase & Activity | Indicative Timeline | Details |
| --- | --- | --- |
| Phase 1: Preparation | January | 4 weeks total |
| 1.1 Questionnaire Development and Approval | Early January (1 week) | Assist the expert in developing thecore questionnaire with MOES and World Bank input. |
| 1.2 Translation to Macedonian and Albanian | Mid-January (1 week) | Translate and review linguistic accuracy. |
| 1.3 Database Setup and Validation | Throughout January | Build and validate graduate database with HE institutions. |
| 1.4 Sample Selection | Late January (1 week) | Assist the expert in drawingq representative sample for phone survey. |
| 1.5 Enumerator Recruitment & Training | End of January (1 week) | Recruit and train enumerators on survey administration. |
| Phase 2: Pilot Testing and Refinement | Late January to Early February | 1 week |
| 2.1 Pilot Test | Early February (1 week) | Pilot test survey, gather feedback, make necessary revisions. |
| Phase 3: Data Collection | February - End March | 8 weeks |
| 3.1 Census Survey (Email) | Early Feb - Mid March | Launch email survey to all graduates with 2 reminders. |
| 3.2 Phone Survey (Sample) | Mid Feb - Mid March | Conduct phone survey with selected sample. |
| Phase 4: Data Cleaning and Quality Control | February – End March | Throughout data collection |
| 4.1 Data Quality Assurance and Coding | Mid - Late March | Check responses, clean data, and code open-ended answers. |
| Phase 5: Data Analysis and Reporting | April – End April | 4 weeks |
| 5.1 Data Analysis | Early - Mid April | Analyze data, including response rates, demographics, etc. |
| 5.2 Report Drafting | Mid April | Draft report with key findings and recommendations. |
| 5.3 Final Report and Submission | End April | Submit finalized report, data files, and documentation. |